## Sheet1
"EduCulture" Defect Report: "Manage User” Module
Defect_ID | Project Name | Summary | Description | Suggestion | Severity | Priority | Type of Defect | Status Valid/Invalid | Reported To | Reported by | Assigned To | CC To | Resolved
Def_ManageUser_01 | EduCulture | search field unable to search user according to entered input by user | when user search for particular user <student ,employee,Admin> by entering valid characters or ID numbers or invalid alphanumeric input values that show all users which are available in record. | it should search only those users whose string matches with string entered by user | low | medium | functional | valid | Vaibhav Sir / Devesh Sir | Rohidas Gaikwad |  |  | Yes
Def_ManageUser_02 | EduCulture | back button on all windows not working properly. | when user move on differenrt windows the back button not working properly . Its unable to redirect user on previous window. |  | low | medium | functional |  | Vaibhav Sir / Devesh Sir | Rohidas Gaikwad |  |  | No
Def_ManageUser_03 | EduCulture | admin profile unable to view. | when user click on view profile link to view the profile for selected admin ,it does not show the profile for that selected user. |  |  |  | functional |  | Vaibhav Sir / Devesh Sir | Rohidas Gaikwad
Def_ManageUser_04 | EduCulture | first name field do not have proper validation. | first name field does not show proper validation. User able to enter alphanumeric strings with symbols. This field shown as a mandatory field till user able to create new user with keeping First Name field blank. No character length validation. | Field should allow to enter only alphabets with specific character length. |  |  | functional |  | Vaibhav Sir / Devesh Sir | Rohidas Gaikwad |  |  | Yes
Def_ManageUser_05 | EduCulture | last name field not have proper validation. | Last name field accept combinations of alphanumeric input and symbols | Last name field should allow user to enter only Alphabets with specific character length. |  |  | functional |  | Vaibhav Sir / Devesh Sir | Rohidas Gaikwad |  |  | Yes
Def_ManageUser_06 | EduCulture | Email-Id field accepts invalid Id. | email Id field does not have proper validation. Email id field does not follow “Regular Expressions” validations. | Email id field should allow user to enter valid email id with specific character length. |  |  | functional |  | Vaibhav Sir / Devesh Sir | Rohidas Gaikwad |  |  | Yes
Def_ManageUser_07 | EduCulture | mandatory fields are not marked by * symbol | user unable to identify the mandatory fields | mandatory fields should marked by * symbol |  |  |  | Invalid | Vaibhav Sir / Devesh Sir | Rohidas Gaikwad |  |  | invalid
Def_ManageUser_08 | EduCulture | 'View Profile' link unable to view Admin users profile | when user click on 'View profile' link on users profile its unable to view profile | [5 empty] | Vaibhav Sir / Devesh Sir | Rohidas Gaikwad
Def_ManageUser_09 | EduCulture | Delete confirmation message has grammatical error | when user click on 'Delete' link to delete Admin profile, it shows confirmation message which has improper sentence format. | [5 empty] | Vaibhav Sir / Devesh Sir | Rohidas Gaikwad
Def_ManageUser_10 | EduCulture | 'Change link on edit users window unable work | 'Change link on edit users window unable work | [5 empty] | Vaibhav Sir / Devesh Sir | Rohidas Gaikwad
[9 empty] | Vaibhav Sir / Devesh Sir | Rohidas Gaikwad
[9 empty] | Vaibhav Sir / Devesh Sir | Rohidas Gaikwad