## Sheet1
"EduCulture" Defect Report: "Settings Module " Date: 22/08/2014, Retested on 10/09/2014
Defect_ID | Project Name | Module Name | Summary | Description | Suggestion | Severity | Priority | Type of Defect | Status Valid/Invalid | Reported To | Reported by | Assigned To | Unresolved Defects | Resolved | Unresolved defects Retested and Verified
Manage Course | [14 empty] | Date: 11/09/2014
Def_Settings_01 | EduCulture | Manage Course | Unnecessary invalid time with course details | when user click on course name from course list , It display course details with course start date and end date along with course created time which is unnecessary | Mandatory fields must be indicated by * sign | low | medium | functional |  | Vaibhav Sir / Devesh Sir | Rohidas Gaikwad |  | Def_Settings_14, Def_Settings_15, Def_Settings_16, Def_Settings_16.1, Def_Settings_16.2, Def_Settings_16.3, Def_Settings_16.4 | yes | Yes
Def_Settings_02 | EduCulture | Manage Course | Course name and section name displayed in different columns | when user click on 'manage Course' link then list of courses dispayed, where coursename and section displayed in different columns, It should be a combined link of 'Course Name' & 'Section' to display course details. |  | low | low | functional |  | Vaibhav Sir / Devesh Sir | Rohidas Gaikwad |  |  | yes | Yes
Def_Settings_03 | EduCulture | Manage Course | "Back" button at different position | On 'Manage Course/Batch' window " Back" button is at right top corner, and on 'Manage course' "Back" button is at left top corner | "Back" button position should be constant on each window. | medium | medium | functional |  | Vaibhav Sir / Devesh Sir | Rohidas Gaikwad |  |  | yes
Def_Settings_04 | EduCulture | Manage Course | when user click on "Save" or "Update" button to save and update changes, it does not display message like ' Course saved/updatd successfully. | when user click on "Save" or "Update" button to save and update cretae d courses user unable to see messages | There should be corresponding messages after completion of Delete or Update functionality | medium | medium | functional |  | Vaibhav Sir / Devesh Sir | Rohidas Gaikwad |  |  | yes
Def_Settings_05 | EduCulture | Manage Course | batch end date smaller than Batch start date saved by user | When user enters batch end date smaller than batch start date, application saved that dates ssccessfully | Batch end date must be greater than batch start date | low | medium | functional |  | Vaibhav Sir / Devesh Sir | Rohidas Gaikwad |  |  | yes
Def_Settings_06 | EduCulture | Manage Course | in list of courses link is not in the format 'Course name + Section' | when user adds different courses, The list of courses is not in form of list of links which has combination of Course name and section |  | low | low | functional |  | Vaibhav Sir / Devesh Sir | Rohidas Gaikwad |  |  | yes
Def_Settings_07 | EduCulture | Manage Course | when user click on link which is combination of ' Course and section' it does not display list of available batches in form of links which is combination of 'Code' and 'Batch name' | when user click on link which is combination of ' Course and section' it does not display list of available batches in the form of links which is combination of 'Code' and 'Batch name' to conduct further functionalities on that batch |  | low | medium |  |  | Vaibhav Sir / Devesh Sir | Rohidas Gaikwad |  |  | yes
Def_Settings_08 | EduCulture | Manage Course | error messages are not in top-down sequences | when user left blank multiple mandatory fields and click to save button, the displayed error messages are not in top-down sequence, last mandatory fields error message display before the previous mandatory fields error message. |  | low | low |  |  | Vaibhav Sir / Devesh Sir | Rohidas Gaikwad |  |  | yes
Def_Settings_09 | EduCulture | Manage Course | wrong placeholder | In initial batch editor window at 'Name' field there is wrong placeholder 'Code' | Each editable field should have correct and appropriate placeholders | medium | medium |  |  | Vaibhav Sir / Devesh Sir | Rohidas Gaikwad |  |  | yes
Def_Settings_10 | EduCulture | Manage Course | "Grading system Type" field is unavailable | When user creating New course, ' Grading system type' field is not available to assign grading type to the course |  | medium | high |  |  | Vaibhav Sir / Devesh Sir | Rohidas Gaikwad |  |  | no
Def_Settings_11 | EduCulture | Manage Course | flow path is not available on each window | when user go through different functionalities, screens the corresponding functional flow path is not dispalyed on the respective screens |  | low | high |  |  | Vaibhav Sir / Devesh Sir | Rohidas Gaikwad |  |  | yes
Def_Settings_12 | EduCulture | Manage Course | "Back" button not available on 'Create Courses' window, | When user click on "New" button to create new course, open window don’t have "Back" button. |  | low | medium |  |  | Vaibhav Sir / Devesh Sir | Rohidas Gaikwad |  |  | yes
Def_Settings_13 | EduCulture | Manage Course | Course name unable to allow spaces | course name unable to accept spaces and length is not defined | field should have validation for: allow only alphabtets, spaces with specified character length 30 characters | medium | high | [6 empty] | yes
Def_Settings_14 | EduCulture | Manage Course | Section name field don’t accept alphanumeric values with symbols | user not able to enter alphanumeric, and special characters (eg. +,-./,#) as input values in section name field | field should accept alphanumeric and special characters as input, with specific character length | medium | medium | [6 empty] | yes
Def_Settings_15 | EduCulture | Manage Course | Code field accept different values as input, it accept arithmetic operators as input value | user able to enter alphanumeric values as a code, it must allow only numbers | There should be proper error message Eg. "Enter only numbers" should have specified character length | medium | high | [6 empty] | yes
Def_Settings_16 | EduCulture | Manage Course | no proper validation for field 'Initial batch name ' | Initial batch name' unable to accept alphanumeric values, sapces and symbols as a input | character length for this field should be specified | low | medium |  |  |  |  | Resolved |  | yes
Def_Settings_16.1 | EduCulture | Manage Course | edit button does not show the confirmation message. | when user “edit” the course, it does not show the the confirmation message “course updated succesfully” | [7 empty] | Resolved |  | yes
Def_Settings_16.2 | EduCulture | Manage Course | “section” field does not accept the alphanumeric symbols. | when user create the new “course”, it show “course was created sucessfully” instead of that it should show “course created sucessfully”. | [9 empty] | yes
Def_Settings_16.3 | EduCulture | Manage Course | In manage course module the code field accept the invalidated characters. | when user enter the code it show the invalidated code field funtionality. | [9 empty] | yes
Def_Settings_16.4 | EduCulture | Manage Course | improper validation for batch field. | when user created the batch, the “batch” field does not show the proper vaildation | [7 empty] | Resolved |  | yes
Manage Batch Module :
Def_Settings_17 | EduCulture | Manage Batch | "Back" button is unavailable on the window | when user click on Manage Batch link, "Back" button is unavailable on the window | Mandatory fields must be indicated by * sign | low | Medium | [5 empty] | Def_Settings_18, Def_Settings_24, Def_Settings_24.1, Def_Settings_24.2, Def_Settings_24.3 | yes
Def_Settings_18 | EduCulture | Manage Batch | Exam' and 'Manage' links of "Manage Batch' are not working | when user select batch from dropdown list, and click on specific batch. Batch open with 'Exam', 'Edit','Delete', and 'Manage' links where 'Exam' and 'Manage' links are not working |  | HIGH | High | [6 empty] | yes
Def_Settings_19 | EduCulture | Manage Batch | on Delete operation, appropriate message are not displayed | when user click on "Delete" button to delete batch, appropriate message noy diaplsyed.(Eg. Course deleted successfully) |  | low | low | [6 empty] | yes
Def_Settings_20 | EduCulture | Manage Batch | when user click on Edit to "update" batch details, appropriate message not displayed | when user click on "Edit" link to change batch details, and click on update button an appropriate message noy diaplsyed.(Eg. Course Updated successfully) |  | low | Medium | [6 empty] | yes
Def_Settings_21 | EduCulture | Manage Batch | search' label is assigned to dropdown box which shows list of corses | Manage Batch' window shows 'Search' text for to select course from dropdown list.(There should be "Select a Course" instead of "Search".) |  | low | Medium | [6 empty] | yes
Def_Settings_22 | EduCulture | Manage Batch | Spelling mistake "Batchs" | when user select course from dropdown list it display available batches in that course. The title 'Batchs' has spell mistake, it should be like 'Batches' |  | low | low | [6 empty] | yes
Def_Settings_23 | EduCulture | Manage Batch | desired contents in link are not displayed | when user select course from dropdown list , its unable to display list of available batches in course as a list of links which having combination of 'Code' and 'Batch name' |  | low | low | [6 empty] | yes
Def_Settings_24 | EduCulture | Manage Batch | when user select batch from specific course, its unable to display students details heading including SI No, Name, Admission Number | when user select batch from specific course, its unable to displaystudents details heading including SI No, Name, Admission Number |  | high | high | [6 empty] | yes
Def_Settings_24.1 | EduCulture | Manage Batch | grammatical mistake in message when user updated the batch. | when user update the batch it shows meaasge ”Batch was sucessfully updated”!! it should be “Batch updated sucessfully.” | [7 empty] | Resolved |  | yes
Def_Settings_24.2 | EduCulture | Manage Batch | “Exams” & “Subject” links does not work correctly. | when user click on “Exam”& “Subject” links,”manage” links does not show the subfield funtionality. | [7 empty] | Resolved |  | yes
Def_Settings_24.3 | EduCulture | Manage Batch | subject link does not show the “subject subfield funtionality”.( such as elective sub ,normal sub.) | when user Edit the field in that the Exam & manage links does not show the sudfield such as ”Add elective subjecrt” & “Add normal subject” | [7 empty] | Resolved |  | yes
Grading Levels
Def_Settings_25 | EduCulture | Grading Levels | Min Score' field unable to accept decimal point values, it allows only whole integer values | Min Score'field allows only whole integer numbers | It should allow decimal point values. (Mandatory fields must be indicated by * sign ) | low | medium | [5 empty] | Def_Settings_25, Def_Settings_27.1 | yes*
Def_Settings_26 | EduCulture | Grading Levels | Min Score' field accept negative numbers and zero | Min Score field accept negative numbers | Min Score must accept only positive numbers >=1 | high | high | [6 empty] | yes
Def_Settings_27 | EduCulture | Grading Levels | Grading Level 'Name' unable to accept spaces | when user creates new grading level, field unable to allow spaces | Field should allow alphanumeric values with spaces. field character length should be defined, because use can enter too long character string | medium | medium | [6 empty] | yes
Def_Settings_27.1 | EduCulture | Grading Levels | save changes button available,but unable to save changes in it. | In batch transfer link when user transfer the selected student batch & click on save changes button it unable to save it. | [9 empty] | yes
Batch Transfer
Def_Settings_28 | EduCulture | Batch Transfer | "Save" button is not available | User able to select batch from specific course, also able to select batch to which students being transferred but "Save" button is not available to save changes | Mandatory fields must be indicated by * sign | high | high |  |  |  |  | Resolved | Def_Settings_28, Def_Settings_30 | yes
Def_Settings_29 | EduCulture | Batch Transfer | Two "Back" buttons on same window | on batch transfer window there are two different"Back" buttons, both buttons have different backward flow |  | high | high | [6 empty] | yes
Def_Settings_30 | EduCulture | Batch Transfer | Graduated batch transfe to former student not working | when user click on 'Graduation' link to transfer students to former batch not working |  | high | HIGH | [6 empty] | no
Student Category
Def_Settings_31 | EduCulture | Student Category | invalid error message | when user enters alphanumeric values in 'Student Category' field, it generates invalid error message "Name allows only letters" | Error message should be "Student category allows only letters" | Medium | Medium | [5 empty] | Def_Settings_31, Def_Settings_32, Def_Settings_33, Def_Settings_35, Def_Settings_36, Def_Settings_37.1, Def_Settings_37.2, Def_Settings_37.3, Def_Settings_37.4 | yes
Def_Settings_32 | EduCulture | Student Category | user unable to enter numbers, spaces and special characters | user unable to enter numbers, spaces and special characters (Eg. SC/ST, NT2 ) | Field should allow /,-._ spaces, alphabets and numbers | medium | high | [6 empty] | yes
Def_Settings_33 | EduCulture | Student Category | Wrong placeholder at 'Enter New Category' field. It is 'Course' | Wrong placeholder at 'Enter New Category' field. It is 'Course' | it should be "Student Category" | low | Medium | [6 empty] | yes
Def_Settings_34 | EduCulture | Student Category | after Save/Delete/ Update operations corresponding messages are not displayed | when user perform operations of Save/Delete/Update, user unable to see corresponding messages (Eg. "Student category Saved/Updated/Deleted successfully ") |  | low | medium | [6 empty] | yes
Def_Settings_35 | EduCulture | Student Category | student category field accept too long character string | user able to enter too long character string | field length should be specified | Medium | Medium |  |  |  |  | Resolved |  | yes
Def_Settings_36 | EduCulture | Student Category | Unable to display error messages | when user click "Edit" button to update student category, when user enters invalid data and click on "Update" button it move to code of that module |  | medium | high |  |  |  |  | Resolved |  | yes
Def_Settings_37 | EduCulture | Student Category | Two "Back" buttons on same window | when user click on "Update" button, new window have two back buttons, while click on both back buttons they redirects on different windows | Mandatory fields must be indicated by * sign | Medium | high |  |  |  |  | Resolved |  | yes
Def_Settings_37.1 | EduCulture | Student Category | Grammatical mistake in message when user create the category. | when user create the category,it show grammatical mistake message “category was sucessfully created”it should be <“category created sucessfully”> | [7 empty] | Resolved |  | yes
Def_Settings_37.2 | EduCulture | Student Category | delete funtionality not working correctiy. | when user delete the specific category it is unable to delete that category,& move on “code” created page | [7 empty] | Resolved |  | yes
Def_Settings_37.3 | EduCulture | Student Category | “enter new category” field able to take long characters string. | when user enter the new category,it takes unlimited string length.it should be upto “25 chatacter “ | [7 empty] | Resolved |  | yes
Def_Settings_37.4 | EduCulture | Student Category | updated funtionality not working correctiy. | when user edit the category,it get edited but it unable to show <“category updated sucessfully”> | [7 empty] | Resolved |  | yes
Manage subject
Def_Settings_38 | EduCulture | Manage Subject | "Back" button unavailable | Manage subject don’t have "Back" button |  | low | medium | [5 empty] | Def_Settings_42, Def_Settings_43, Def_Settings_44
Def_Settings_39 | EduCulture | Manage Subject | wrong label 'Search' assigned for | Search' label is used for dropdown box, when user going to select a batch | label should be "Select a Batch" | low | medium | [6 empty] | yes
Def_Settings_40 | EduCulture | Manage Subject | Subject Name field do not allow arithmetic operators and special symbols | Subject Name field do not allow arithmetic operators and special symbols (Eg. Subject: C++, C#) | Subject Name field should allow Alphabets, numbers,spaces and symbols | medium | medium | [6 empty] | yes
Def_Settings_41 | EduCulture | Manage Subject | Max Weekly classes field allow zero values and negative numbers | Max Weekly classes field allow zero values and negative numbers | it must allow only positive numbers, greater than zero | medium | high | [6 empty] | yes
Def_Settings_42 | EduCulture | Manage Subject | transper | when user create elective subject and define max weekly classes, field allows negative numbers |  | medium | high | [6 empty] | yes
Def_Settings_43 | EduCulture | Manage Subject | Normal Subject/ Elective group/ Elective subject created successfully messages are not generated | when user create, adds normal subject/Elective group/ Elective subject corresponding messages are unable to display | messages should be: 1)Normal subject added successfully. 2)New Elective group added successfully, 3)New Elective subject added successfully | medium | medium | [6 empty] | yes
Def_Settings_44 | EduCulture | Manage Subject | elective subject name field unable to accept special symbols | elective subject name field unable to accept special symbols. | elective subject name should allow alphabets, numbers, spaces and symbols | medium | high | [6 empty] | yes
Def_Settings_45.1 | EduCulture | Manage Subject | user unable to enter subject name with one or two characters | when user enter the subject name it unable to accept single or two characters. | user should able to enter subject name Eg. C, C++ which has one or two characters, Manage subject field should have validation where field should allow subject name=>1 characters | [8 empty] | yes
General Settings
Def_Settings_46 | EduCulture | General Settings | Institution name field allows only 15 characters | many times institution names are too long, so user should be unable to enter school/Clollege names with long character strings | Mandatory fields must be indicated by * sign | high | very high |  |  |  |  | Resolved | Def_Settings_46, Def_Settings_47, Def_Settings_48, Def_Settings_50, (Def_Settings_49 allow user to enter negative numbers ) | yes
Def_Settings_47 | EduCulture | General Settings | mandatory fields are not indicated by * sign | user not able to differentiate mandatory and optional fields | mandatory fields should be indiacated by * sign | medium | high |  |  |  |  | Resolved |  | yes
Def_Settings_48 | EduCulture | General Settings | Error messages should have spaces in the text | when user enters invalid input, error messages are generated. The text of error messages does not havae spaces |  | low | medium | [6 empty] | yes
Def_Settings_49 | EduCulture | General Settings | phone number field allow decimal point numbers, allows too long numbers, and multiple zeros | when user enters phone number ,field allow to save decimal point numbers, multiple zeros and too long numbers, It alloews negative numbers | phone number field must allow only numbers, with specific length | medium | high | [6 empty] | yes
Def_Settings_50 | EduCulture | General Settings | when user update general settings, it does not show message like"General settings updated successfully." | when user updates general settings, user unable to |  | low | high | [6 empty] | yes
Add Additional Details and SMS Module from Settings module are incompleted.