## Sheet1
"EduCulture" Defect Report: "Manage User” Module
Defect_ID | Project Name | Summary | Description | Suggestion | Severity | Priority | Type of Defect | Status Valid/Invalid | Reported To | Reported by | Assigned To | CC To | Resolved | confirmation by testers | new defects by review 10
Def_ManageUser_01 | EduCulture | search field unable to search user according to entered input by user | when user search for particular user <student ,employee,Admin> by entering valid characters or ID numbers or invalid alphanumeric input values that show all users which are available in record. | it should search only those users whose string matches with string entered by user | low | medium | functional | valid | Vaibhav Sir / Devesh Sir | Rohidas Gaikwad |  |  | Yes | resolved
Def_ManageUser_1.1 | EduCulture | label should be search users instead of search label. | when user search for specific user,user should know that what to search.so label should be search users instead of search label. |  | low | low | functional | valid | Vaibhav Sir / Devesh Sir | Rohidas Gaikwad |  |  |  |  | Def_ManageUser_1.1
Def_ManageUser_02 | EduCulture | back button on all windows not working properly. | when user move on differenrt windows the back button not working properly . Its unable to redirect user on previous window.(back button not working properly.) |  | low | medium | functional |  | Vaibhav Sir / Devesh Sir | Rohidas Gaikwad |  |  | No |  | Def_ManageUser_02
Def_ManageUser_03 | EduCulture | admin profile unable to view. | when user click on view profile link to view the profile for selected admin ,it does not show the profile for that selected user.(thisprofile is of display only the small window adminprofile.) |  |  |  | functional |  | Vaibhav Sir / Devesh Sir | Rohidas Gaikwad |  |  | Yes | resolved
Def_ManageUser_04 | EduCulture | first name field do not have proper validation. | first name field does not show proper validation. User able to enter alphanumeric strings with symbols. This field shown as a mandatory field till user able to create new user with keeping First Name field blank. No character length validation. | Field should allow to enter only alphabets with specific character length. |  |  | functional |  | Vaibhav Sir / Devesh Sir | Rohidas Gaikwad |  |  | Yes | resolved
Def_ManageUser_05 | EduCulture | last name field not have proper validation. | Last name field accept combinations of alphanumeric input and symbols | Last name field should allow user to enter only Alphabets with specific character length. |  |  | functional |  | Vaibhav Sir / Devesh Sir | Rohidas Gaikwad |  |  | Yes | resolved
Def_ManageUser_06 | EduCulture | Email-Id field accepts invalid Id. | email Id field does not have proper validation. Email id field does not follow “Regular Expressions” validations. | Email id field should allow user to enter valid email id with specific character length. |  |  | functional |  | Vaibhav Sir / Devesh Sir | Rohidas Gaikwad |  |  | Yes | resolved
Def_ManageUser_07 | EduCulture | mandatory fields are not marked by * symbol | user unable to identify the mandatory fields | mandatory fields should marked by * symbol |  |  |  | Invalid | Vaibhav Sir / Devesh Sir | Rohidas Gaikwad |  |  | invalid |  | Def_ManageUser_07
Def_ManageUser_08 | EduCulture | 'View Profile' link unable to view Admin users profile | when user click on 'View profile' link on users profile its unable to view profile | [5 empty] | Vaibhav Sir / Devesh Sir | Rohidas Gaikwad |  |  | No |  | Def_ManageUser_08
Def_ManageUser_09 | EduCulture | Delete confirmation message has grammatical error | when user click on 'Delete' link to delete Admin profile, it shows confirmation message which has improper sentence format. | [5 empty] | Vaibhav Sir / Devesh Sir | Rohidas Gaikwad |  |  | yes |  | Def_ManageUser_09
Def_ManageUser_10 | EduCulture | 'Change password link on edit users window unable work | 'Change Password link on edit users window unable work | [5 empty] | Vaibhav Sir / Devesh Sir | Rohidas Gaikwad |  |  | yes | resolved